SciRet — Final Research Plan

Post-Rebuttal Gap-Closing Revision (Scoped Path)

Status: active | Last updated: 2026-07-31 | Submission 8722, ARR

Companion working files (project folder → reboot_plan/): SciRet_Reboot_Plan.md (live checklist), SciRet_Reboot_Log.md (change history)

# 1. Where We Are

SciRet (ARR Submission 8722, “SciRet: A Compute-Aware Empirical Study of Retrieval and Reranking for Scientific RAG”) went through ARR review in early July 2026. All three reviews are summarized below.

| Reviewer | Soundness / Excitement | Overall Assessment | Headline concern |
| --- | --- | --- | --- |
| R1 (5KS8) | 4 / 4 | 2.5 — Borderline Findings | Query set 15-query sourcing, overlap, and validation unclear |
| R2 (SPUz) | 2.5 / 2.5 | 2.5 — Borderline Findings | Pseudo-label circularity, single dataset/generator/reranker |
| R3 (VbPC) | 2 / 2 | 2 — Resubmit next cycle | Statistical power, reranker baseline confounds, reproducibility (2/1/1) |

Author replies (SciRet_Author_Replies_v2.docx) were submitted 2026-07-10/11, committing to specific fixes per reviewer. Rebuttal is complete. This document is the single source of truth for what “closing the gaps” means for the next submission and how we're doing it — it replaces every earlier reboot-plan draft (see the change log).

Open item: memory on file describes a 2026-07-11 decision to commit the current paper as-is to EMNLP 2026 by Aug 2, 2026, with the gap-closing work below intended as the fallback path if that submission is not accepted (notification ~Aug 20, 2026), expanding into a full paper for arXiv rather than another ARR cycle. Confirm this is still the live plan before treating the timeline below as unconstrained.

# 2. Scope Decision

Two directions existed in earlier drafts of this plan:

1. Scoped revision — fix exactly what R1/R2/R3 raised: statistical rigor, an added reranker baseline, recall@K reporting, reproducibility, limitations writing, and an optional TREC-COVID, BioASQ anchor check.

2. Full rebuild (“SciRet-Verify”) — multimodal evidence-unit retrieval, claim-level citation verification, a new codebase, and 5 new datasets (SciFact, QASPER, PubMedQA, SPIQA, TREC-COVID).

Decision (2026-07-31): scoped revision. It's what the actual reviewers asked for, it's achievable without a ground-up rebuild, and every commitment already made in the rebuttal falls inside it. The full-rebuild ideas are not discarded — they are archived in the Appendix as future-paper material, not part of this submission's plan.

# 3. Gap Inventory, By Angle

Each table below lists the gap, who raised it, what was already promised in the rebuttal (if anything), and what closing it actually require.

## 3.1 Statistical Rigor

| Gap | Raised by | Rebuttal commitment / status | What's needed |
| --- | --- | --- | --- |
| No significance testing on retrieval/reranking comparisons, especially given only 15 queries | R2, R3 | “bootstrap confidence intervals on the retrieval tables given the small query set” | Paired bootstrap CIs (or significance test) on Recall@K and Precision@K tables. Re-run from existing per-query score files — no new retrieval runs needed. |
| Query set too small (15) for statistical power | R1, R2, R3 | “expanding to a stratified 50-query set balanced across six themes (imaging, molecular/mechanistic, clinical outcomes, treatment, methodology, cross-domain synthesis)” | Real work: draft ~35 new queries across the 6 themes, label them the same way as the original 15, and re-run retrieval/generation/RAGAS on the full 50-query set at all three scales. Single biggest lift in the plan. |

## 3.2 Baselines

| Gap | Raised by | Rebuttal commitment / status | What's needed |
| --- | --- | --- | --- |
| Single MS MARCO reranker — can't separate “domain mismatch” from “this reranker” | R2, R3 | “add at least one scientific/biomedical reranker in the revision” | Pick and run ≥1 scientific/biomedical cross-encoder (SciBERT/PubMedBERT-based, or a BGE reranker fine-tuned on biomedical pairs). Report precision@K and recall@K alongside MS MARCO and no-rerank. |
| Reranking: only precision reported, not recall | R2 | “recall@K alongside precision@K ... will add it in the revision” | Compute recall@K before/after reranking from stored run outputs. Cheap — no new inference. |
| Single generator (GPT-4o-mini only) | R2 | Scope explicitly to “in our setup”; flag other-LLM generalization as future work | Writing only: tighten scope language, add explicit future-work sentence. |

## 3.3 Data / Evaluation-Label Integrity

| Gap | Raised by | Rebuttal commitment / status | What's needed |
| --- | --- | --- | --- |
| Pseudo-relevance labels come from the same hybrid system being evaluated (circularity) | R1, R2 | “add a TREC-COVID qrel overlap check for a subset of queries in the revision” | Pull TREC-COVID qrels, find query overlap with our query set, report agreement between our pseudo-labels and official qrels. Moderate effort; addresses the core critique directly. |
| Why isn't hybrid R@3 = 1.0 at 1K/5K if top-3 hybrid defines relevance? | R1 | Explained: labels fixed from 15K-scale hybrid results; smaller corpora don't contain all 3 labeled docs | Writing only — add this explanation to Section 3.4 (Retrieval Evaluation Note). Not yet in current main.tex. |
| R@1 denominator (max 1/3) — why still meaningful? | R2 | Explained in rebuttal (relative signal within our labeling protocol, not an absolute benchmark) | Writing only — add the explanation sentence (text already drafted in the rebuttal reply). |
| Mean chunk tokens (215) constant across all scales | R2 | Explained: same chunking parameters regardless of corpus size | Writing only — add clarifying sentence near the dataset statistics table. |
| CORD-19 version/filtering not specified | R2 | Not yet answered — needs KB input | Once KB confirms which release/date and filtering, add one sentence to Section 3.1. |
| 15-query sourcing, cross-scale overlap, topical skew | R1 | Partially answered: queries developed iteratively, same 15 used at all scales, no formal skew check run | Covered by the 50-query expansion in 3.1 — new set is stratified by theme so coverage is checkable. |

## 3.4 Generalization

| Gap | Raised by | Rebuttal commitment / status | What's needed |
| --- | --- | --- | --- |
| Single dataset (CORD-19 only) | R2 | Flag as untested generalization in Limitations | Writing: add explicit Limitations sentence. Optional stretch (not committed): test a second scientific domain. |
| No discussion of generalizability beyond COVID-19, data/language bias, equity, broader societal impact | R2 (Limitations & Societal Impact) | Not directly promised, but flagged as missing | Writing only: expand Limitations/Ethics — CORD-19's English-language/journal skew, who is/isn't served, misinformation/over-reliance risk without expert oversight. No new experiments. |

## 3.5 Evaluation Methodology / Generation Quality

| Gap | Raised by | Rebuttal commitment / status | What's needed |
| --- | --- | --- | --- |
| RAGAS metrics not defined/discussed; no human eval or fact verification | R3 | “short definitions plus a discussion of known LLM-judge biases”; ethics statement's medical-use warning as partial mitigation | Writing: add RAGAS metric-definition paragraph + LLM-judge bias discussion. Human eval is optional/future work, not committed. |
| Context precision very low (0.095–0.122), unexplained | R2 | Explained: RAGAS context precision here is citation-based (fraction of retrieved passages the generator actually cites, not relevance) | Writing: current paper text does not match the committed explanation — needs correcting to the citation-based framing. |
| No failure-case / qualitative analysis | R2 | Not committed | Optional stretch: 2–3 qualitative examples. Not required for this pass. |
| Chunking analysis only at 1K scale, brief | R2 | Not committed | Optional/low priority — defer. |

## 3.6 Reproducibility & Release

| Gap | Raised by | Rebuttal commitment / status | What's needed |
| --- | --- | --- | --- |
| Reproducibility 2, Datasets 1, Software 1 scores — release commitments unclear | R3 | “add a dedicated Reproducibility section with direct links to the dataset, code repository, and pre-built index artifacts” | Needs KB input: confirm actual repo URL / hosting for code + index artifacts. CORD-19 source link (github.com/allenai/cord19) already known. |

## 3.7 Framing / Editorial

| Gap | Raised by | Rebuttal commitment / status | What's needed |
| --- | --- | --- | --- |
| Paper reads as short report, scope/depth mismatch for a conference paper | R2 | Make “controlled empirical comparison, short-paper track by design” framing explicit up front, per rebuttal | Writing task. |
| Typos: abstract spacing, “each retriever,” text[[...]] artifact, “and 1 others” citations | R2 | Done | Verified against current main.tex — nothing further needed. |

# 4. Priority Order (Highest Leverage First)

1. Stratified 50-query expansion (3.1) — biggest lift, unlocks everything downstream

2. Scientific/biomedical reranker baseline (3.2) — most-requested addition, appears in 2 reviews

3. Recall@K for reranking (3.2) — cheap, directly requested

4. Bootstrap CIs / significance tests (3.1) — cheap once per-query scores exist for the 50-query set

5. TREC-COVID qrel anchor check (3.3) — moderate effort, addresses the core circularity critique directly

6. Writing-only fixes (3.3, 3.4, 3.5, 3.7) — label-construction note, R@1 explanation, chunk-token note, context-precision correction, generalization/equity Limitations, RAGAS definitions, scope framing

7. Reproducibility section (3.6) — blocked on KB confirming release links

8. CORD-19 version sentence (3.3) — blocked on KB confirming version/filtering

Item 1 gates items 2–5 in practice: reranker comparison, recall@K, bootstrap CIs, and the TREC-COVID check should all be computed on the final (50-query) evaluation set rather than redone twice, unless an interim result on the original 15 is shipped first. See Section 8 for phased sequencing.

# 5. Explicitly Out of Scope for This Pass

- New pipeline architecture, multimodal evidence units, claim-level citation verifier, adaptive retrieval router — all part of the archived full-rebuild direction (Appendix).

- Second dataset / cross-domain generalization test — optional stretch only, not committed to reviewers.

- Human evaluation study — optional stretch only, not committed to reviewers.

- Qualitative failure-case analysis — optional stretch only.

# 6. Open Questions Needing KB's Input

These block specific writing tasks and can't be resolved by re-reading existing files:

1. CORD-19 version/filtering — which release/date, filtered to peer-reviewed only or not? (blocks 3.3 CORD-19 version sentence)

2. Code/index release location — actual repo URL and where pre-built indexes are hosted? (blocks 3.6 Reproducibility section)

3. Third co-author — name, order, affiliation for the human-verification contributor mentioned 2026-07-31 (blocks author list finalization; see main.tex)

4. Target venue / EMNLP 2026 commitment status — confirm whether the Aug 2, 2026 EMNLP commitment (per prior decision on file) is still happening, and whether this document is the fallback plan for a post-rejection expansion or an independent track.

# 7. Authors

Restored 2026-07-31 (was “Anonymous ACL submission” for blind review):

- Kaysarul Anas Apurba — Laurentian University

- Md. Hasibul Hasan — Laurentian University (corresponding, kaysarulanas2@gmail.com)

- [third co-author — human-verification contribution — TBD]

main.tex currently also carries a header marking it “Preprint — Work in Progress,” consistent with treating this as a de-anonymized working copy rather than a blind-review submission.

Reminder: if the next submission target turns out to be another double-blind venue, main.tex will need to be re-anonymized (author names removed, Acknowledgments re-blinded) before submission.

# 8. Step-by-Step Plan

Mirrors the live checklist in SciRet_Reboot_Plan.md — update that file as the working source of truth; this section is a point-in-time snapshot for sharing.

### Phase 0 — Housekeeping (2026-07-31)

☐  Consolidate all reboot-plan docs into the research approach + step-by-step plan + log — DONE

☐  Restore real author names in SciRet_ARR_2026/main.tex — DONE

☐  KB: confirm CORD-19 version/filtering used

☐  KB: confirm code/index release repo URL

☐  KB: confirm third co-author name, order, affiliation

☐  KB: confirm EMNLP 2026 commitment status / target venue

Decision gate: Docs consolidated, author names restored, open KB questions logged.

### Phase 1 — Expand the Query Set (do first)

☐  Draft ~35 new queries across the 6 committed themes (imaging, molecular/mechanistic, clinical outcomes, treatment, methodology, cross-domain synthesis)

☐  Review new queries for phrasing skew (avoid favoring sparse or dense retrieval)

☐  Generate pseudo-relevance labels using the same method as the original 15 (15K-scale hybrid top-3, held fixed across scales)

☐  Re-run retrieval (BM25, dense, hybrid) for all 50 queries at 1K/5K/15K scales

☐  Re-run generation + RAGAS for all 50 queries at all scales

☐  Store per-query score files (needed for bootstrap CIs)

Decision gate: Retrieval and generation results exist for the full 50-query set at all three scales, stored for per-query statistical analysis.

### Phase 2 — Reranker Baseline

☐  Short model search: identify ≥1 scientific/biomedical cross-encoder reranker candidate

☐  Run the new reranker on the same retrieval outputs used for the MS MARCO comparison

☐  Report precision@K and recall@K for: no-rerank, MS MARCO, new scientific reranker

☐  Update the reranking table in main.tex

Decision gate: Paper can state whether the MS MARCO degradation was reranker-specific or a general domain-mismatch effect.

### Phase 3 — Recall@K for Reranking

☐  Compute recall@K before/after reranking from stored run outputs

☐  Add recall@K columns/table alongside the existing precision@K table

Decision gate: Reranking analysis reports both precision and recall, as requested by R2.

### Phase 4 — Statistical Rigor

☐  Compute paired bootstrap CIs (or significance test) for the retrieval comparisons

☐  Compute the same for the reranking precision/recall comparisons

☐  Document the bootstrap method (resampling procedure, number of resamples, CI level)

☐  Add CIs to the relevant tables or a supplementary table

Decision gate: Every headline retrieval/reranking claim has an associated CI or significance statement.

### Phase 5 — TREC-COVID Qrel Anchor Check

☐  Pull TREC-COVID qrels

☐  Match the 50 queries against TREC-COVID topics (exact or near-duplicate)

☐  For the overlapping subset, compare pseudo-relevance labels against official qrels

☐  Write up the result as an external validity check

Decision gate: Paper cites an external anchor point for the pseudo-label methodology, not just an internal disclosure.

### Phase 6 — Writing-Only Fixes (No New Experiments)

☐  Section 3.4: label-construction explanation (why hybrid R@3 < 1.0 at 1K/5K)

☐  Add R@1 denominator explanation

☐  Add chunk-token stability explanation near the dataset statistics table

☐  Correct the context-precision explanation to the citation-based framing

☐  Add RAGAS metric definitions + LLM-judge bias discussion

☐  Expand Limitations: generalizability, data/language bias, equity, societal impact

☐  Make “short paper track, controlled empirical comparison” framing explicit in the Introduction

☐  Once KB confirms CORD-19 version/filtering: add the sentence to Section 3.1

Decision gate: Every writing commitment made in the rebuttal is reflected in main.tex.

### Phase 7 — Reproducibility Section

Blocked on KB confirming the repo URL / index hosting location (Phase 0).

☐  Add a dedicated Reproducibility section with direct links to CORD-19, the SciRet code repo, and pre-built index artifacts

Decision gate: Reproducibility/Datasets/Software concerns from R3 are directly addressed with working links.

### Phase 8 — Final Pass

☐  Re-verify typo/citation fixes are still correct after all edits above

☐  Full read-through against the rebuttal to confirm every commitment was kept

☐  Recompile main.tex; check for overfull boxes / broken references after new tables

☐  Update abstract if headline numbers changed (50-query results may differ from the original 15-query numbers)

☐  Final author-block check: names present, or re-anonymized if the target venue requires blind review

Decision gate: Every commitment made in the rebuttal is verifiably kept in the submitted paper.

## Stretch / Optional (Not Committed to Reviewers)

Do only if time allows, in this order:

☐  Second scientific-domain dataset for generalization

☐  Small human evaluation of generation quality

☐  2–3 qualitative failure-case examples

☐  Extend chunking analysis across all scales (currently 1K only)

# Appendix — Archived: Full-Rebuild Direction (“SciRet-Verify”)

Kept for future reference only — not part of the current plan. If this submission is accepted, or the team later decides to expand into a full paper, this is the direction scoped out on 2026-05-22.

Working title: SciRet-Verify: Evidence-Centric Multimodal Retrieval-Augmented Generation for Scientific Question Answering

Core thesis: Scientific RAG systems should be evaluated not just on whether they produce plausible answers, but on whether each answer claim can be traced to and verified against the correct scientific evidence unit.

### Four Linked Contributions Envisioned

1. Evidence-unit indexing — typed units (abstract, section paragraph, table, figure, caption, equation, citation context) instead of title/abstract-only chunks.

2. Adaptive retrieval router — route queries to lexical, dense, late-interaction, visual-page, table-aware, or citation-graph retrieval.

3. Claim-level citation verifier — decompose answers into atomic claims, check each against cited evidence (entailment/contradiction/insufficient), track numeric and modality-mismatch errors.

4. Cross-dataset benchmark — TREC-COVID/CORD-19, PubMedQA, SciFact, QASPER, SPIQA, ChartQA instead of CORD-19 only.

Why parked: too large a scope change for the current review cycle; none of the three reviewers asked for a new architecture — they asked for the existing study to be more statistically sound, more thoroughly baselined, and more honest about generalization limits. That's a revision, not a rebuild.

If revisited later: start from a Research Lock phase — finalize contribution statement, dataset list, and evaluation metrics before writing any new code. Sources consulted for that direction (ColPali, VisRAG, GraphRAG, RAGAS, MIRAGE, MTRAG, mmRAG, PubMedQA, QASPER, TREC-COVID, SciFact, SPIQA, ChartQA) are preserved in the removal record in SciRet_Reboot_Log.md.