SciRet - Team Kickoff Brief

Prepared for the 2026-08-05 meeting

Goal: get SciRet accepted at a top NLP venue. Path: revise and resubmit to the October 2026 ARR cycle (deadline Oct 12, 2026), aiming to commit to NAACL 2027 / COLING 2027.

# 1. Where the project stands

SciRet (“A Compute-Aware Empirical Study of Retrieval and Reranking for Scientific RAG”) was submitted to ARR as Submission 8722 and reviewed in early July 2026. It was not accepted outright, but none of the reviewers asked for a different paper — they asked for the existing study to be more statistically sound, more thoroughly baselined, and more honest about its limits.

That's a revision, not a rebuild, and it's achievable before the October cycle.

| Reviewer | Scores | Verdict | Headline ask |
| --- | --- | --- | --- |
| R1 | Soundness 4, Excitement 4 | 2.5 — Borderline Findings | Clarify query sourcing/overlap across scales |
| R2 | Soundness 2.5, Excitement 2.5 | 2.5 — Borderline Findings | Pseudo-label circularity; single dataset/generator/reranker |
| R3 | Soundness 2, Excitement 2 | 2 — Resubmit next cycle | Statistical power; reranker confound; reproducibility (2/1/1) |

Author replies (rebuttal) were submitted 2026-07-10/11 and made specific commitments per reviewer - those commitments are what this plan closes out.

# 2. The team

Four co-authors as of 2026-08-04:

- Kaysarul Anas Apurba — Laurentian University — lead / corresponding author

- Md. Hasibul Hasan — Laurentian University

- Rofiqul Alam Shehab — North South University — joined for the human-verification contribution

- Asab Azad — Laurentian University — newest addition

# 3. What needs to happen (the gap list)

Everything below is either explicitly promised in the rebuttal or directly requested by a reviewer. Full detail with reviewer quotes lives in SciRet_Research_Approach.md; this is the condensed version for discussion.

1. Expand the 15-query evaluation set to a stratified 50 across six themes — biggest single lift, gates several other tasks.

2. Add a second (scientific/biomedical) reranker baseline — most-requested addition, raised by two reviewers.

3. Report recall@K for reranking, not just precision — cheap, direct request.

4. Add real statistical significance testing (not just raw numbers) to every headline comparison.

5. Add an external anchor (TREC-COVID qrels) to validate the pseudo-relevance labels — addresses the core methodological critique.

6. Writing-only fixes to main.tex — DONE as of 2026-08-04.

7. Add a Reproducibility section with real links once the repo is confirmed public.

Not in scope for this pass: a full multimodal/claim-verification rebuild, a second dataset, or a formal human evaluation study — those are optional stretch goals only if time allows.

# 4. Proposed work division (draft — confirm today)

This is a starting proposal based on how the tasks split naturally, not a final assignment. Rofiqul was already discussed for a human-verification-shaped role; the rest is open for discussion based on who wants to do what.

| Phase | What it delivers | Proposed owner | Est. effort |
| --- | --- | --- | --- |
| Phase 1 Query expansion | Draft ~35 new queries across 6 themes (imaging, molecular/mechanistic, clinical outcomes, treatment, methodology, cross-domain synthesis) to reach 50 total; label them; re-run retrieval + generation at all 3 scales. | AAzad | Largest single task |
| Phase 2 Reranker baseline | Find and run ≥1 scientific/biomedical cross-encoder reranker; compare against MS MARCO reranker and no-rerank. | KAApurba | High (ML engineering) |
| Phase 3 Recall@K | Compute recall@K before/after reranking from existing run outputs. | Md. Hasibul Hasan | Low (fast win) |
| Phase 4 Statistical rigor | Shapiro-Wilk → paired t-test or Wilcoxon, Cohen's d, bootstrap 95% CIs on all headline retrieval/reranking comparisons. | MHHasan | Medium |
| Phase 5 TREC-COVID anchor check | Pull TREC-COVID qrels, match against our query set, compare our pseudo-labels to official relevance judgments. | RAShehab | Medium |
| Phase 6 Writing fixes | All 7 rebuttal-committed text edits to main.tex. DONE as of 2026-08-04. | KAApurba (done) | Complete |
| Phase 7 Reproducibility section | Confirm the public repo has code/indexes; write a Reproducibility section with direct links. | KA Apurba | Low-medium |
| Phase 8 Final pass | Recompile, verify every rebuttal commitment is met, generate the anonymized ARR-submission copy, submit by Oct 12. | Whole team | Coordination |

# 5. Questions to settle in this meeting

☐ Does the proposed work division above match actual interests/availability?

☐ Is the GitHub repo (github.com/anaskaysar/sciret) public and populated with code/indexes yet? Phase 7 depends on this.

☐ What’s everyone's realistic weekly time budget between now and Oct 12?

☐ Any preference on compute access for Phase 1/2 (Kaggle free tier, personal GPU, etc.)?

☐ Confirm co-authorship expectations (order is currently Apurba, Hasan, Shehab, Azad — open to revisit based on final contribution).

# 6. After this meeting

Once assignments are confirmed, update SciRet_Reboot_Plan.md with final owners and add a dated log entry in SciRet_Reboot_Log.md capturing what was decided. Each phase has its own decision gate (defined in the plan) so it's clear when a task is done, not just started.